## Slide 1
CYCLECAD SUITE
Development Plan
How we convert today’s monolithic cycleCAD + ExplodeView + Pentacad apps into ~114 Lego-shaped widgets — each independently runnable, each with its own test suite — all running over one shared kernel.
~50,000
lines of monolithic code today
~114
planned Lego widgets
11
widget categories
8
phases · strangler-fig migration
Sachin Kumar · cyclecad.com · 2026

## Slide 2
cycleCAD Suite — Development Plan
01 / MENTAL MODEL
cycleCAD Suite Development Plan · v1.0
2 / 12
Every feature lands in one of four buckets
No grey area. Before we touch any code we decide: is this a widget, a workflow, library code, or app shell?
WIDGET
Most things become this
Has UI surface or callable API. Mounts somewhere. Has init() / destroy().
Examples: cam-nav · dro · ai-render · gcode-editor · explode-slider · section-cut · admin-overview
WORKFLOW
JSON chain of widget calls
Multi-step combinations of widgets. Token-priced as bundle.
Examples: hero-shot pipeline · manufacturability scan · CAM-to-machine · onboarding tour
LIBRARY
Pure code, no DOM, no kernel
Imported by widgets. Three.js, OCCT WASM, geometry math, constraint solver, NURBS.
Lives in shared/lib/ — never gates the meter, never mounts.
APP SHELL
The baseplate HTML
Tiny — ~150 lines per app after migration. Declares which widgets to load via manifest.json. Snaps blocks together.
cycleCAD · ExplodeView · Pentacad · admin
The rule: if it has UI or an API call, it’s a widget. If it chains widgets, it’s a workflow. If it’s pure math or a parser, it’s a library. Everything else is the app shell.

## Slide 3
cycleCAD Suite — Development Plan
02 / TAXONOMY
cycleCAD Suite Development Plan · v1.0
3 / 12
The widget catalogue · ~114 blocks
Eleven categories. Counting features that already exist across cycleCAD, ExplodeView, Pentacad. Many are duplicated 3 × today — the refactor dedupes them.
Category
Examples
Source app(s)
#
Universal 3D
viewport · cam-nav · grid · axes · lights · picking
all 3 apps
6
Sketch
sketch-line · circle · rect · arc · polyline · constraint-solver
cycleCAD
7
Solid ops
extrude · revolve · sweep · loft · hole · thread · fillet · chamfer · shell · pattern…
cycleCAD
15
Surface / sheet
t-spline · nurbs · sheet-bend · flange · unfold
cycleCAD
5
Assembly
mate · joint · motion-study · explode-slider · interference · contact-set
cycleCAD + ExplodeView
6
Visualization
wireframe · blueprint · transparency · section-cut · isolate · fit · screenshot
all 3
8
Analysis
measure · weight · part-compare · FEA · thermal · modal · DFM · ai-engineer-analyst
cycleCAD + ExplodeView
10
AI
ai-copilot · ai-render · ai-narrator · ai-vision-id · ai-chatbot · ai-search-nl · batch-scan
all 3
7
I/O
STEP · GLB · STL · OBJ · glTF · DXF · PDF · BOM-CSV · DWG · OCCT-WASM
all 3
10
CAM
contour · pocket · drill · adaptive · post · gcode-editor · sim · bridge · jog · dro · playback
Pentacad
14
Documentation
annotations · qr · manual · tech-report · standards-id · mcmaster-search · kiri-moto
ExplodeView
8
Admin
overview · users · api-keys · tokens · audit · registry-edit · stats · health · realtime…
admin app (new)
18
TOTAL
after migration, every cross-app duplicate becomes ONE widget loaded by all apps that need it
114

## Slide 4
cycleCAD Suite — Development Plan
03 / STRATEGY
cycleCAD Suite Development Plan · v1.0
4 / 12
Strangler-fig migration — the apps stay shipping
No big-bang rewrite. Pull one feature out of the monolith. Land it as a widget. Delete the old code. Repeat ~114 times.
1
Pick a feature
one row off the migration matrix · the simplest yet-undone widget
2
Extract
pull code from app.js into widgets/<name>.js · keep behaviour bit-identical
3
Wrap as widget
add init/destroy/api · pass meter · register in manifest
4
Test in isolation
build demo + spec · ≥5 assertions · dashboard goes green
5
Delete old code
remove the original from app.js · app shell now thinner
REPEAT → every step ships green → app.js shrinks one feature at a time → ~114 widgets later, app shell is empty
RULES
1. Every commit leaves all apps shipping. Never two failing apps at once. 2. Behaviour stays identical during extraction. Refactor for cleanliness only after the widget is green. 3. Cross-app dedupe FIRST. Anything in 2+ apps is the highest-priority extraction.

## Slide 5
cycleCAD Suite — Development Plan
04 / WIDGET CONTRACT
cycleCAD Suite Development Plan · v1.0
5 / 12
Each widget = 5 files. Each ships with its own test suite.
No widget is "done" until all five rows are green. The test suite is non-negotiable — every widget proves it works in isolation.
/widgets/<name>.js
implementation — ESM single file, exports init(opts) → {api, on, destroy}
/tests/widgets/<name>.html
standalone demo — bare HTML page that mounts the widget on a real host scene
/tests/widgets/<name>.spec.html
test suite — ≥5 automated assertions + leak test, posts spec-result to parent
/shared/widget-registry.js
manifest entry — { name, tier, minRole, freeQuota, cost, deps }
/tests/index.html
dashboard row flips from ‘stub’ → ‘live’ once spec passes
THE TEST CONTRACT — every spec must cover
1. init() returns valid handle (api object · on function · destroy function) 2. mounts expected DOM into the host 3. every public api method is callable + emits expected events 4. destroy() cleans up DOM, Three.js, listeners, timers 5. 5 init/destroy cycles do not leak DOM or memory

## Slide 6
cycleCAD Suite — Development Plan
05 / TEST SUITES
cycleCAD Suite Development Plan · v1.0
6 / 12
Tested like Lego — every widget proves itself in isolation
Open one HTML file in any browser. Watch the spec run. See the result post to the dashboard. No build step, no CI dependency.
PER-WIDGET FILE STRUCTURE
widgets/ cam-nav.js ← implementation dro.js ai-render.js ... tests/widgets/ cam-nav.html ← standalone demo cam-nav.spec.html ← test suite (5+) dro.html dro.spec.html ... tests/index.html ← dashboard, aggregates spec-result postMessages
DASHBOARD — tests/index.html
Run all
cam-nav
live
7/7
dro
live
10/10
gcode-editor
stub
explode-slider
stub
ai-render
stub
playback
stub
section-cut
planned
...

## Slide 7
cycleCAD Suite — Development Plan
06 / PHASES
cycleCAD Suite Development Plan · v1.0
7 / 12
Eight phases
Strangle the monolith one feature at a time. Each phase ends with a green dashboard, a thinner monolith, and more widgets in the registry.
0
Inventory
FEATURE-MIGRATION-PLAN.md — ~150 rows × 3 apps mapping every feature to a target widget
OUT single source of truth
1
Foundation widgets
viewport · cam-nav · dro (✓) · grid · axes · widget-registry · CONTRACT.md
OUT apps can mount onto kernel
2
Cross-app dedupe FIRST
section-cut · explode-slider · fit-to-selection · screenshot · BOM · ai-render · chatbot · hero-shot · measure
OUT ~25 widgets, 3-app reuse
3
cycleCAD-only
sketch · solid · surface · assembly ops — ~33 widgets replace sections of cycleCAD app.js
OUT cycleCAD shell thinner
4
ExplodeView-only
AR mode · ai-narrator · animated-instructions · nl-search · maint-heatmap · wear-timeline · service-mode
OUT ExplodeView shell thinner
5
Pentacad-only
7 CAM strategies · post-processor · sim-executor · rockhopper-bridge · jog-pad · machine-picker
OUT Pentacad shell thinner
6
Admin app
18 admin widgets in 3 waves — overview · users · tokens · audit · registry-edit · stats · health …
OUT operator dashboard live
7
Workflows + retire
JSON workflows + bundle discounts. Delete old app.js files. Each app = thin manifest + shell.
OUT monolith retired

## Slide 8
cycleCAD Suite — Development Plan
07 / DECISIONS
cycleCAD Suite Development Plan · v1.0
8 / 12
Critical decisions — made up front so the migration doesn’t drift
Every refactor calls for a few opinionated choices. Locking these in saves hundreds of small re-decisions later.
Who owns the 3D viewport?
A `viewport` widget. Apps treat it as a singleton. Other widgets receive scene/camera/controls as opts. Same shape cam-nav already uses.
What is NOT a widget?
Three.js itself, OCCT WASM, OCC.js, geometry/math, constraint solver, NURBS, parsers. These are libraries (`shared/lib/`). No kernel involvement.
How do existing apps stay alive during migration?
A `bridge.js` shim lets the old monolith call new widgets. Bridge gets deleted at phase 7. Strangler-fig means apps NEVER break.
Token economics during migration?
Most read-only widgets stay free (cam-nav, dro, sketch, section-cut). Heavy compute pays (ai-render 500, FEA 1000, CAM gen 300, ai-engineer 200). Per-call meter goes paid only at phase 7.
Behavioural diff between apps for the SAME feature?
Migration matrix has a "behaviour diff" column for each cross-app widget. Surface differences early; pick a winner; document why.
Where do widget-specific assets live?
Static deps stay alongside the widget: `widgets/<name>.js` + optional `widgets/<name>.css` + `widgets/<name>/<assets>`. Loader resolves relative paths.

## Slide 9
cycleCAD Suite — Development Plan
08 / RISKS
cycleCAD Suite Development Plan · v1.0
9 / 12
Risks — named and mitigated
Refactors die when nobody writes the risks down. Here are the five that could derail us, and how each gets defused.
HIGH
Migration takes 6+ months and apps break mid-flight
→
Strangler fig — every commit ships a working app. Never two failing at once. Bridge shim isolates.
MED
Widget contract too narrow for some features
→
Add escape hatches early (viewport.attach, controls passthrough). Refine the contract slot-by-slot, document each.
MED
Token economics feel punitive on previously-free features
→
Most features stay free in the registry. Only NEW heavy compute pays. Free quota generous. Admin bypass for testing.
LOW
Three.js / OCCT version drift between apps
→
Pin in shared/lib/, single import map across the suite. CI check (when CI lands) verifies versions match.
MED
Cross-app dedupe reveals subtle behaviour differences
→
Migration matrix has a per-widget "behaviour diff" column. Decide winner up front. Track losers as feature flags during cutover.
HIGH
Solo-founder bus factor
→
Every doc lives in the repo. HANDOFF.md is canonical. Each widget self-documents (impl + demo + spec). Onboarding is `git clone && npm i`.

## Slide 10
cycleCAD Suite — Development Plan
09 / NEXT
cycleCAD Suite Development Plan · v1.0
10 / 12
Next six deliverables — in this order
Land these and the migration is unblocked. Each one is small, atomic, and gets pushed.
1
FEATURE-MIGRATION-PLAN.md
→
The inventory — ~150 rows × 3 apps. Source feature → target widget → priority → behaviour diff. Single source of truth.
2
shared/widget-registry.js
→
Formal manifest with { name, tier, minRole, freeQuota, cost, deps } for every planned widget. Token economics live here.
3
shared/CONTRACT.md
→
Formal widget-contract spec. Promote the inline draft to canonical. Every widget gets validated against it.
4
widgets/viewport.js
→
The universal 3D substrate. Once this lands, every other 3D widget can attach to it. Architectural keystone.
5
widgets/section-cut.js
→
First shared-across-3-apps proof. Pull it from cycleCAD, run standalone, then have ExplodeView + Pentacad load the SAME widget.
6
walking the migration matrix
→
From here, work down the inventory in priority order. Each row = one widget. ~5–10 widgets per week sustainable cadence.

## Slide 11
cycleCAD Suite — Development Plan
10 / CADENCE
cycleCAD Suite Development Plan · v1.1
11 / 12
Two-stage build — skeleton, then widgets
Stage 1 lands the kernel + app shells + test runner + Docker stack as a single push. Stage 2 ships widgets one at a time — you test each, then we move to the next.
STAGE 1
Skeleton — one push
~1 day of work · single combined commit
shared/CONTRACT.md + widget-registry.js + auth.js stub
4 app shells (cycleCAD · ExplodeView · Pentacad · admin)
tests/runner.html + tests/CONTRACT.md
workflows/workflow.schema.json + runner stub
server/meter (Fastify · fakes ledger) + bridge stub
docker-compose.yml + INSTALL.md + CONTRIBUTING.md
GREEN-LIGHT GATE — you sign off Stage 1 before Stage 2 begins
STAGE 2
Widgets — one at a time
~115 widgets · you set the pace · 12 categories
1. I write impl + demo + spec + registry entry
2. I push (single combined command in your clipboard)
3. You open the demo + spec, test it
4. GREEN → I flip dashboard to "live", start next widget
5. ISSUES → I fix, push, you re-test
6. Last widget in category? Review category as a whole
GREEN-LIGHT GATE — per-widget · you confirm before next
COMMITMENT no widget moves to "live" without your explicit thumbs-up. You hold the pace. Every push is fully reviewable.

## Slide 12
Built like Lego.
Tested like Lego.
Shipped like Lego.
Every widget runs alone. Every widget tests itself. Every widget gets a green dashboard row before the next one begins.
$CYCLE — pay-per-widget · admin runs free
cyclecad.com · github.com/vvlars-cmd/cyclecad-suite